## Schedule
Task# | Description | Start Date | End Date | Duration in Days | Days Passed | Days Left | Effort Hours Estimate | Effort Hours Complete | Effort Hours Left | Input | Output | Responsible | Status
| Total --> |  |  | 706 | 35 | 40 | 43.5 | 7.5 | 36
001 | Project Start and End Dates | 2024-01-29 | 2024-04-13 | 75
002a | Project Proposal | 2024-02-06 | 2024-02-16 | 10 |  |  | 3 | 3 | 0 | I1, I2, I3, … | O1, O2, … | R1, R2, … | Complete
002b | Project Proposal Resubmission | 2024-02-21 | 2024-04-13 | 52 |  |  | 1 | 0.5 | 0.5 | I1, I2, I3, … | O1, O2, … | R1, R2, … | In Progress
003 | Create and maintain schedule | 2024-02-27 | 2024-04-13 | 46 |  |  | 2 | 0.5 | 1.5 | I1, I2, I3, … | O1, O2, … | R1, R2, … | In Progress
004 | List of User Stories | 2024-02-20 | 2024-04-13 | 53 |  |  | 3 |  | 3 |  |  |  | Not Started
005 | Graphical and textual description of the software architecture | 2024-03-04 | 2024-04-13 | 40 |  |  | 1 |  | 1 |  |  |  | Not Started
006 | Graphical and textual description of the software design | 2024-03-04 | 2024-04-13 | 40 |  |  | 1 |  | 1 |  |  |  | Not Started
007 | Source Code | 2024-03-04 | 2024-04-13 | 40 |  |  | 10 |  | 10 |  |  |  | Not Started
008 | Test cases and results | 2024-03-18 | 2024-04-13 | 26 |  |  | 4 |  | 4 |  |  |  | Not Started
009 | Create install instructions | 2024-03-18 | 2024-04-13 | 26 |  |  | 2 |  | 2 |  |  |  | Not Started
010 | Create tool list/description | 2024-03-04 | 2024-04-13 | 40 |  |  | 2 |  | 2 |  |  |  | Not Started
011 | Create user manual | 2024-03-04 | 2024-04-13 | 40 |  |  | 2 |  | 2 |  |  |  | Not Started
012 | Create minutes documents | 2024-02-06 | 2024-04-13 | 67 |  |  | 1.5 | 0.5 | 1 |  |  |  | In Progress
013 | Bi-Weekly status report meetings | 2024-02-12 | 2024-04-13 | 61 |  |  | 2 | 1 | 1 |  |  |  | In Progress
014 | Functioning product | 2024-03-25 | 2024-04-13 | 19 |  |  | 1 |  | 1 |  |  |  | Not Started
015 | Create presentation slides | 2024-03-25 | 2024-04-13 | 19 |  |  | 2 |  | 2 |  |  |  | Not Started
016 | Create lessons learned | 2024-03-25 | 2024-04-13 | 19 |  |  | 1 |  | 1 |  |  |  | Not Started
017 | Use "Evaluation of Installation of the Registry System" | 2024-03-25 | 2024-04-13 | 19 |  |  | 2 |  | 2 |  |  |  | Not Started
018 | Create intital product backlog | 2024-02-20 | 2024-03-05 | 14 |  |  | 3 | 2 | 1 |  |  |  | In Progress
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
Formulas:
Days Passed = TODAY() -[Start Date, row below]
Days Left = [End Date, row below]-TODAY()