## Schedule
Task# | Description | Start Date | End Date | Duration in Days | Days Passed | Days Left | Effort Hours Estimate | Effort Hours Complete | Effort Hours Left | Input | Output | Responsible | Status
| Total --> |  |  | 699 | 72 | 0 | 86 | 86 | 0
001 | Project Start and End Dates | 2024-02-06 | 2024-04-18 | 72
002a | Project Proposal | 2024-02-06 | 2024-02-16 | 10 |  |  | 3 | 3 | 0 | I1, I2, I3, … | O1, O2, … | R1, R2, … | Complete
002b | Project Proposal Resubmission | 2024-02-21 | 2024-04-18 | 57 |  |  | 1 | 1 | 0 | I1, I2, I3, … | O1, O2, … | R1, R2, … | Complete
003 | Create and maintain schedule | 2024-02-27 | 2024-04-18 | 51 |  |  | 2 | 2 | 0 | I1, I2, I3, … | O1, O2, … | R1, R2, … | Complete
004 | List of User Stories | 2024-02-20 | 2024-04-18 | 58 |  |  | 3 | 3 | 0 |  |  |  | Complete
005 | Graphical and textual description of the software architecture | 2024-03-04 | 2024-04-18 | 45 |  |  | 3 | 3 | 0 |  |  |  | Complete
006 | Graphical and textual description of the software design | 2024-03-04 | 2024-04-18 | 45 |  |  | 3 | 3 | 0 |  |  |  | Complete
007 | Source Code | 2024-03-04 | 2024-04-18 | 45 |  |  | 15 | 15 | 0 |  |  |  | Complete
008 | Test cases and results | 2024-03-25 | 2024-04-18 | 24 |  |  | 3 | 3 | 0 |  |  |  | Complete
009 | Create install instructions | 2024-04-08 | 2024-04-18 | 10 |  |  | 2 | 2 | 0 |  |  |  | Complete
010 | Create tool list/description | 2024-03-04 | 2024-04-18 | 45 |  |  | 2 | 2 | 0 |  |  |  | Complete
011 | Create user manual | 2024-04-08 | 2024-04-18 | 10 |  |  | 3 | 3 | 0 |  |  |  | Complete
012 | Create minutes documents | 2024-02-06 | 2024-04-18 | 72 |  |  | 1.5 | 1.5 | 0 |  |  |  | Complete
013 | Bi-Weekly status report meetings | 2024-02-12 | 2024-04-18 | 66 |  |  | 5 | 5 | 0 |  |  |  | Complete
014 | Functioning product | 2024-03-25 | 2024-04-18 | 24 |  |  | 15 | 15 | 0 |  |  |  | Complete
015 | Create presentation slides | 2024-04-08 | 2024-04-18 | 10 |  |  | 3 | 3 | 0 |  |  |  | Complete
016 | Create lessons learned | 2024-04-08 | 2024-04-18 | 10 |  |  | 2 | 2 | 0 |  |  |  | Complete
017 | Use "Evaluation of Installation of the Registry System" | 2024-04-17 | 2024-04-18 | 1 |  |  | 0.5 | 0.5 | 0 |  |  |  | Complete
018 | Create intital product backlog | 2024-02-20 | 2024-03-05 | 14 |  |  | 3 | 3 | 0 |  |  |  | Complete
019 | Set up database environment | 2024-03-04 | 2024-03-22 | 18 |  |  | 8 | 8 | 0 |  |  |  | Complete
020 | Working Draft of Project | 2024-03-20 | 2024-04-01 | 12 |  |  | 8 | 8 | 0 |  |  |  | Complete
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
|  |  |  | 0 |  |  |  |  | 0
Formulas:
Days Passed = TODAY() -[Start Date, row below]
Days Left = [End Date, row below]-TODAY()