## Test Cases
User Story ID | User Story | Test Case ID | Test Case Description | Pre-conditions | Test Steps | Test Data | Expected Result | Actual Result | Test Date | Tested by | Test Status (Pass/Fail) | Defect Description | Description of defect resolution | Additional Comments
LOGIN01 | As a user, I want to login to Wishlister | LOGIN01.TC01 | Enter valid User Name and valid Password | 1. Need a valid Wishlister Account to do login | 1. Enter User Name | <Valid User Name> | Successful login | Successfully logged in the home page | 2024-04-10 | Lane Meadows | Pass | None | None
[5 empty] | 2. Enter Password | <Valid Password>
3. Click "Login" button
LOGIN01 | As a user, I want to login to Wishlister | LOGIN01.TC02 | Enter valid User Name and invalid Password | 1. Need a valid Wishlister Account to do login | 1. Enter User Name | <Valid User Name> | A message "Username or Password does not match" is shown | A message "Username/Password is incorrect" is shown | 2024-04-10 | Lane Meadows | Pass | None | None
[5 empty] | 2. Enter Password | <Invalid Password>
3. Click "Login" button
LOGIN01 | As a user, I want to login to Wishlister | LOGIN01.TC03 | Enter invalid User Name and valid Password | 1. Need a valid Wishlister Account to do login | 1. Enter User Name | <Invalid User Name> | A message "Username or Password does not match" is shown | A message "Username/Password is incorrect" is shown | 2024-04-10 | Lane Meadows | Pass | None | None
[5 empty] | 2. Enter Password | <Valid Password>
3. Click "Login" button
LOGIN01 | As a user, I want to login to Wishlister | LOGIN01.TC04 | Enter invalid User Name and invalid Password | 1. Need a valid Wishlister Account to do login | 1. Enter User Name | <Invalid User Name> | A message "Username and Password does not match" is shown | A message "Username/Password is incorrect" is shown | 2024-04-10 | Lane Meadows | Pass | None | None
[5 empty] | 2. Enter Password | <Invalid Password>
3. Click "Login" button
MRP01 | As a new user, I would like to create an account, so that I can save my lists. | MRP01.TC01 | Enter valid fields |  | 1. Enter input fields | <Valid data> | Successful registration | Successfully logged in and able to create a list | 2024-04-10 | Lane Meadows | Pass | None | None
2. Click Register
MRP01 | As a new user, I would like to create an account, so that I can save my lists. | MRP01.TC02 | Enter invalid fields |  | 1. Enter input fields | <Invalid data> | Failed registration | Failed to register | 2024-04-10 | Lane Meadows | Pass | None | None
2. Click Register
MRP02 | As a new user, I would like to personalize my account with a unique user/pass, so that I can login. | MRP02.TC01 | Enter custom valid Username and valid Password during registration |  | 1. Enter User Name | <Valid Username> | Successful registration | Successfully logged in and able to look at all the pages | 2024-04-10 | Lane Meadows | Pass | None | None
[5 empty] | 2. Enter Password | <Valid Password>
[5 empty] | 3. Confirm Password | <Valid Password>
4. Click Register
MRP02 | As a new user, I would like to personalize my account with a unique user/pass, so that I can login. | MRP02.TC02 | Enter custom valid Username and invalid Password during registration |  | 1. Enter User Name | <Valid Username> | Failed registration | Failed registration and message pops up "Passwords do not match" | 2024-04-10 | Lane Meadows | Pass | None | None
[5 empty] | 2. Enter Password | <Invalid Password>
[5 empty] | 3. Confirm Password | <Invalid Password>
4. Click Register
MRP02 | As a new user, I would like to personalize my account with a unique user/pass, so that I can login. | MRP02.TC03 | Enter custom invalid Username and valid Password during registration |  | 1. Enter User Name | <Invalid User Name> | Failed registration | Failed registration | 2024-04-12 | Lane Meadows | Pass | None | None
[5 empty] | 2. Enter Password | <Valid Password>
[5 empty] | 3. Confirm Password | <Valid Password>
4. Click Register
MRP03 | As someone concerned with security, I would like to create a password, so that I can protect my info. | MRP03.TC01 | A vaild password can be entered during registration |  | 1. Enter Password | <Valid Password> | Successful registration | Successfully logged in | 2024-04-12 | Lane Meadows | Pass | None | None
2. Click Register
MRP03 | As someone concerned with security, I would like to create a password, so that I can protect my info. | MRP03.TC02 | An invaild password can not be entered during registration |  | 1. Enter Password | <Invalid Password> | Failed registration | Failed registration | 2024-04-12 | Lane Meadows | Pass | None | None
2. Click Register
MRP04 | As a user with an account, I would like to be able to update my password, so that I can login if I forget it. | MRP04.TC01 | A vaild password can be entered to sucessfully change password during reset | 1. Need a valid Wishlister Account to attempt password reset | 1. Enter Password | <Valid Password> | Successful password change and login | Successful password change and login | 2024-04-12 | Lane Meadows | Pass | None | None
2. Update Password
3. Updated password works for login
MRP04 | As a user with an account, I would like to be able to update my password, so that I can login if I forget it. | MRP04.TC02 | An invaild password can not be entered during password reset | 1. Need a valid Wishlister Account to attempt password reset | 1. Enter Password | <Invalid Password> | Password change unsuccessful | Password change unsuccessful | 2024-04-12 | Lane Meadows | Pass | None | None
2. Update Password
MRP06 | As someone concerned with security, I would like to be able to update my password, so that I can protect my info. | MRP06.TC01 | A vaild password can be entered to sucessfully change password | 1. Need a valid Wishlister Account to attempt password reset | 1. Enter Password | <Valid Password> | Successful password change and login | Successful password change and login | 2024-04-12 | Lane Meadows | Pass | None | None
2. Update Password
3. Updated password works for login
MRP06 | As someone concerned with security, I would like to be able to update my password, so that I can protect my info. | MRP06.TC02 | An invaild password can not be entered during password change | 1. Need a valid Wishlister Account to attempt password reset | 1. Enter Password | <Invalid Password> | Password change unsuccessful | Password change unsuccessful | 2024-04-12 | Lane Meadows | Pass | None | None
2. Update Password
MRP07 | As someone viewing a users lists, I would like to view them without logging in, so that I can purchase the gifts anonymously. | MRP07.TC01 | A wishlist can be viewed without signing in by searching with a valid username | 1. Need a valid Wishlister wishlist to have been created | 1. Browse to "Search a Wishlist" |  | Wishlists can be viewed without signing in | Succesful to search a wishlist without signing in | 2024-04-12 | Lane Meadows | Pass | None | None
[5 empty] | 2. Enter Username wishlist owner | <Valid Username>
3. Click search
MRP07 | As someone viewing a users lists, I would like to view them without logging in, so that I can purchase the gifts anonymously. | MRP07.TC02 | A wishlist can not be viewed without signing in by searching with an invalid username | 1. Need a valid Wishlister wishlist to have been created | 1. Browse to "View a Wishlist" |  | Wishlists can not be viewed | That user does not exist, please check your spelling and try again. | 2024-04-13 | Lane Meadows | Pass | None | None
[5 empty] | 2. Enter Username wishlist owner | <Invalid Username>
3. Click search
MRP13 | As a developer, I want to create a database that can store links, so a list of items can be created. | MRP13.TC01 | The database is storing lists and allows items to be added to a list | 1. Need a valid Wishlister Account logged in | 1. Browse to "Create a Wishlist" |  | Lists are created and list items are stored correctly, so both can be viewed after creation | Lists are created and stored correctly, can be viewed | 2024-04-13 | Lane Meadows | Pass | None | None
[5 empty] | 2. Create a wishlist | <Valid data>
[5 empty] | 3. Add items to wishlist | <Valid data>
4. Items can be viewed after added to list
MRP16 | As a developer, I want to link a database to account, so that users can store their lists. | MRP16.TC01 | The database is storing lists, allowing for post-creation viewing | 1. Need a valid Wishlister Account logged in | 1. Browse to "Create a Wishlist" |  | Lists are created and stored correctly, so they can be viewed after creation | Lists are created and stored correctly, can be viewed | 2024-04-13 | Lane Meadows | Pass | None | None
[5 empty] | 2. Create a wishlist | <Valid data>
3. List can be viewed after creation from "View a Wishlist"
MRP17 | As a developer, I want to create a user friendly UI, so that users can easily create, access, and manage their lists. | MRP17.TC01 | All features (Create, View, Manage) are usuable | 1. Need a valid Wishlister Account logged in | 1. Browse to "Create a Wishlist" |  | All Features load and work | All features load and work correctly | 2024-04-13 | Lane Meadows | Pass | None | None
2. Browse to "View a Wishlist"
3. Edit a Wishlist
MRP18 | As a developer, I want to save a user's login, so they can access their save lists later. | MRP18.TC01 | User's logins are saved with a list allowing post-creation access and management | 1. Need a valid Wishlister Account logged in | 1. Browse to "Create a Wishlist" |  | Wishlists are accessable by the creator after creation | Wishlists are accessable by the creator after creation | 2024-04-14 | Lane Meadows | Pass | None | None
[5 empty] | 2. Create a wishlist | <Valid data>
3. List can be viewed after creation from "View a Wishlist"
MRP18 | As a developer, I want to save a user's login, so they can access their save lists later. | MRP18.TC02 | User's logins are saved with a list not allowing post-creation access and management by anyone besides the creator |  | 1. Browse to "Search a Wishlist" while not signed in as the list creator |  | Wishlists are unmodifiable by anyone beside the creator | Wishlists can only be modified by the creator | 2024-04-15 | Lane Meadows | Pass | None | None
2. Search Wishlist
3. Attempt to modify wishlist
MRP19 | As a friend of a user, I would like to mark a gift as purchased, so that only one is gifted. | MRP19.TC01 | A guest can search a list, view the list, and mark list items as purchased |  | 1. Browse to "Search a Wishlist" while not signed in as the list creator |  | Wishlist items can be marked as purchased, and change appearance after being marked | Items can be marked purchased or not purchased | 2024-04-15 | Lane Meadows | Pass | None | None
2. Search Wishlist
3. Mark an item as purchased in wishlist
MRP27 | As a user, I want to be able to create a list, so that I can save items I want. | MRP27.TC01 | A user can create a wishlist and save items | 1. Need a valid Wishlister Account logged in | 1. Browse to "Create a Wishlist" |  | A wishlist can be created and items can be added to the wishlist | Wishlist can be created and items can be added | 2024-04-15 | Lane Meadows | Pass | None | None
[5 empty] | 2. Create a wishlist | <Valid data>
[5 empty] | 3. Add items to wishlist | <Valid data>
MRP28 | As a user, I want to be able to share a list with friends, so they can purchase items for me. | MRP28.TC01 | Wishlists can be viewed by users besides the wishlist creator |  | 1. Browse to "Search a Wishlist" while not signed in as the list creator |  | Wishlist is visible | Wishlist is visible | 2024-04-15 | Lane Meadows | Pass | None | None
[5 empty] | 2. Search Wishlist with wishlist creator's username | <Valid data>
MRP29 | As a user, I want to add items from my favorite sites, so that I save them as a list. | MRP29.TC01 | Links can be added as a wishlist item | 1. Need a valid Wishlister Account logged in | 1. Browse to "View a Wishlist" |  | Add a link as an item to the list | A link can be added and is diplayed as "Item number" | 2024-04-15 | Lane Meadows | Pass | None | None
|  |  |  | 2. Need a wishlist created | 2. Edit a Wishlist
[5 empty] | 3. Add link as item on wishlist | <Valid data>
MRP31 | As a developer, I want to link a database to an html website, so that I can access the database through the UI. | MRP31.TC01 | The database is working by storing lists and list items | 1. Need a valid Wishlister Account logged in | 1. Browse to "Create a Wishlist" |  | Lists are created and list items are stored correctly, so both can be viewed after creation | Lists are created and items are stored correctly in database | 2024-04-15 | Lane Meadows | Pass | None | None
[5 empty] | 2. Create a wishlist | <Valid data>
[5 empty] | 3. Add items to wishlist | <Valid data>
4. Items can be viewed after added to list
MRP32 | As a developer, I want to update a database from a html website, so the User can create and manage lists. | MRP32.TC01 | The database is storing lists and allows items to be added to a list | 1. Need a valid Wishlister Account logged in | 1. Browse to "Create a Wishlist" |  | Lists are created and list items are stored correctly, so both can be viewed after creation | The database is storing the items correctly after creation | 2024-04-15 | Lane Meadows | Pass | None | None
[5 empty] | 2. Create a wishlist | <Valid data>
[5 empty] | 3. Add items to wishlist | <Valid data>
4. Items can be viewed after added to list
MRP33 | As a user, I want to be able to delete a list, so that once an event is over I can free up space. | MRP33.TC01 | A wishlist can be deleted by the wishlist creator | 1. Need a valid Wishlister Account logged in | 1. Browse to "View a Wishlist" |  | Wishlist should be deleted | Wishlist can be deleted by creator | 2024-04-15 | Lane Meadows | Pass | None | None
|  |  |  | 2. Need a wishlist created | 2. Delete wishlist
3. Update List and refresh the page
MRP33 | As a user, I want to be able to delete a list, so that once an event is over I can free up space. | MRP33.TC02 | A wishlist can not be deleted by anyone besides the wishlist creator |  | 1. Browse to "Search a Wishlist" while not signed in as the list creator |  | Wishlist should not be able to be deleted | Wishlist cannot be deleted by an external user | 2024-04-15 | Lane Meadows | Pass | None | None
2. Search Wishlist
3. Attempt to delete wishlist
MRP35 | As an external user, I would like the UI to be user friendly, so that I can easily access a list. | MRP35.TC01 | Lists can be accessed from the "View a wishlist" page | 1. Need a valid Wishlister Account logged in | 1. Browse to "View a Wishlist" |  | List(s) are visible | Creators lists are visible and able to edit them | 2024-04-15 | Lane Meadows | Pass | None | None
2. Need a wishlist created
MRP35 | As an external user, I would like the UI to be user friendly, so that I can easily access a list. | MRP35.TC02 | Lists can be accessed from the "Search a wishlist" page | 1. Need a wishlist created | 1. Browse to "Search a Wishlist" |  | List(s) are visible | Lists are visible if you search for a creator | 2024-04-15 | Lane Meadows | Pass | None | None
2. Enter Username of wishlist creator
MRP36 | As a new user, I would want to find a registration option easily accessible from the homepage. | MRP36.TC01 | Is "Register" Button visible | 1. No pre-conditions | 1. Browse to "Home" |  | Register button should be visible | Register button is visible and easily accessible from the homepage | 2024-04-15 | Lane Meadows | Pass | None | None
MRP37 | As a new user, I would like a clear and intuitive registration form with fields for entering a username, email address, and password. | MRP37.TC01 | Username, email address, and password fields are initially blank when registering | 1. No pre-conditions | 1. Click "Register" |  | Input fields should be blank | Input fields are blank when you first click on the register button | 2024-04-15 | Lane Meadows | Pass | None | None
MRP38 | As a new user, I would like to see a prominent "Register" or "Sign Up" button on the homepage for quick access to the registration page. | MRP38.TC01 | Is "Register" Button visible | 1. No pre-conditions | 1. Browse to "Home" |  | Register button should be visible | Register button is visible on the top and bottom of the homepage | 2024-04-15 | Lane Meadows | Pass | None | None
MRP39 | As a registered user, I would like a clean and intuitive login form with fields for entering my username/email and password. | MRP39.TC01 | Username and password fields are initially blank when attempting to login | 1. No pre-conditions | 1. Click "Login" |  | Input fields should be blank | Input fields are blank when you first click on the login button | 2024-04-15 | Lane Meadows | Pass | None | None
MRP40 | As a user, I would like the login page to have a link to the registration page for new users to sign up. | MRP40.TC01 | Login page has a working "Register" button | 1. Be on the login page | 1. Click "Login" |  | "Register" button on the login page should redirect to register page | "Register" button on the login page does redirect to the register page | 2024-04-15 | Lane Meadows | Pass | None | None
2. Click "Register"
MRP41 | As a user, I would like to delete items off my list after I created the list, so nobody will buy an item i don't want | MRP41.TC01 | User can delete an item off their list after creating it. | 1. Need a valid Wishlister Account logged in | 1. Browse to "View a Wishlist" |  | The item that the user deleted will be deleted from their list forever | The item has been deleted from the list | 2024-04-17 | Lane Meadows | Pass | None | None
|  |  |  | 2. Need a wishlist created | 2. Delete item
2. Click Update list
MRP42 | As a user, I would like to be able to add items after i created the list, so i can add more items. | MRP42.TC01 | User can add an item to their list after creating it. | 1. Need a valid Wishlister Account logged in | 1. Browse to "View a Wishlist" |  | The item that the user adds to their list will be add to the list | The item has been added to the list | 2024-04-17 | Lane Meadows | Pass | None | None
|  |  |  | 2. Need a wishlist created | 2. Add item
3. Click Update list